## Sheet1
Project Expense Tracking Template (NGN)
live Cost Control Register, tracking actual spend against your approved budget for better financial oversight.
S/N | Date | WBS Category | Item Description (Detailed) | Budgeted Total Cost (NGN) | Actual Unit Cost (NGN) | Actual Quantity | Commitment/LPO Amount (NGN) | Actual Paid Amount (NGN) | Cost Variance (NGN) | Document Reference (Invoice/PV) | Notes/Justification
1 | - | H/R (Manpower) | - | 1366000 | 797500 | - | 0 | 878000 | - | - | -
1.1 | 2025-11-10 | H/R | Project Engineer (Week 1 Salary) | 300000 | 300000 | 1 L/S | - |  | 300000 | PV-PE-M1 | Paid monthly
1.2 |  | H/R | AutoCAD Engineer (Week 1 Salary) | 70000 | 70000 | 1 L/S | - | 70000 | 0 | PV-AE-M1 | Paid monthly
1.3 |  | H/R | QHSE Officer (Week 1 Salary) | 250000 | 250000 | 1 L/S | - | 250000 | 0 | PV-QO-M1 | Paid monthly
1.4 | 11/14/2025, 11/18/2025, 11/21/2025 | H/R | Iron Bender (Week 1 Salary) | 60000 | 12000 | 5 days |  | 50000 | 10000 | PV-IB-D1 | paid daily
1.5 |  | H/R | Mason (Week 1 Salary) | 50000 | 12500 | 4 days | - |  | 50000 | PV-MASON-D1 | paid daily
1.6 | 2025-11-26 | H/R | Welder / Fabricator (Week 1 Salary) | 180000 | 15000 | 12 days | - | 80000 | 100000 | PV-WF-D | paid daily
1.7 |  | H/R | Electrician Technician (Week 1 Salary) | 45000 | 15000 | 3 days | - | 50000 | -5000 | PV-ET-D1 | paid daily
1.8 | 11/12/2025, 11/13/2025, 11/14/2025, 11/15/2025, 11/17/2025, 11/19/2025, 11/20/2025, 11/21/2025, 11/24/2025, 11/25/2025, 11/28/2025, 11/29/2025, 12/02/2025, 12/04/2024, 12/06/2025, 12/8/2025,12/9/2025,12/10/2025, 12/11/2025, 12/12/2025 | H/R | Helper / Labourer (Daily payment) | 256000 | 8000 | 32 days |  | 255000 | 1000 | PV-HL-D1 | paid daily
1.9 |  | H/R | Equipment Operator (Week 1 Salary) | 40000 | 20000 | 2 days | - |  | 40000 | PV-EO-D1 | paid daily
1.1 | 11/25/2025, 11/27/2025, 12/01/2025 | H/R | Roof installers (Week 1 Salary) | 75000 | 25000 | 3 days |  | 75000 | 0 | PV-RI-D0 | paid daily
1.11 | 12/8/2025,12/09/2025, 12/10/2025 | H/R | Pipe Fitter (Week 1 Salary) | 40000 | 40000 | 1 Days | - | 48000 | -8000 | PV-PI-D1 | paid daily
1.12 | 11/15/2025, 11/17/2025, 11/29/2025, | HR | Capenter | 30000 | 30000 | L/S ( UNBUDGETED) |  | 30000 | 0
SUB-TOTALS |  |  |  | 1366000 | 797500 |  | 0 | 908000 | 488000
S/N | Date | WBS Category | Item Description (Detailed) | Budgeted Total Cost (NGN) | Actual Unit Cost (NGN) | Actual Quantity | Commitment/LPO Amount (NGN) | Actual Paid Amount (NGN) | Cost Variance (NGN) | Document Reference (Invoice/PV) | Notes/Justification
2 | - | Material Requirements | - | 4952200 | 511549.976 | - | - | 3216599.8499 | 1735600.1501 | - | -
2.1 | 2025-11-10 | Material | Elephant Ordinary Portland Cement (OPC) | 336000 | 10050 | 32 | PAID | 321600 | 14400 | INV-SUP-001 | DEPOSITED CHEQUE ( cleared )
2.2 | 2025-11-12 | Material | River Sand | 105000 | 47000 | 1 |  | 47000 | 58000 | INV-SUP-002
2.3 | 2025-11-12 | Material | Granite Chippings | 304000 | 315000 | 1 |  | 315000 | -11000 | INV-SUP-003
|  |  | Reinforcement Bars(10mm) |  | 7400 | 1
|  |  | Reinforcement Bars (12mm) |  | 8900 | 16
|  |  | Reinforcement Bars (16mm) |  | 15900 | 1
2.4 | 2025-11-10 | Material | Reinforcement Bars (Avg. 10/12/16mm) | 261000 | 32200 | 5.1335 | Paid | 165299.9999 | 95700.0001 | INV-SUP-004 | DEPOSITED CHEQUE (cleared)
2.5 | 2025-11-10 | Material | Binding Wire (Gauge 16) | 9000 | 10000 | 1 | PAID | 10000 | -1000 | INV-SUP-005 | DEPOSITED CHEQUE ( cleared)
2.6 | 2025-11-12 | Material | Formwork Boards (3/4" marine board) | 90000 | 25000 | 2 |  | 50000 | 40000 | INV-SUP-006
2.7 | 2025-11-18 | Material | Anchor Bolts / Expansion Bolts (M16-M20) | 220000 | 2800 | 20 |  | 56000 | 164000 | INV-SUP-007
2.8 | 2025-11-18 | Material | I-Beams/H-Beams (Galv. 100x150mm) | 375000 | 17272.72 | 11 |  | 189999.92 | 185000.08 | INV-SUP-008
2.9 | 2025-11-18 | Material | Base Plates (12mm thick steel) | 90000 | 9500 | 4 |  | 38000 | 52000 | INV-SUP-009
|  |  | Angle Iron (60 x 60 x 5) |  | 11818.18 | 16.5
|  |  | Angle Iron (50 x 50 x 5) |  | 8181.81 | 38.5
|  |  | Angle Iron (40 x 40 x 5) |  | 6363.636 | 88
2.1 | 2025-11-18 | Material | Angle Iron (mm) | 943000 |  | 115 |  | 766000 | 177000 | INV-SUP-010
2.11 | 2025-11-18 | Material | U-channel | 519000 | 16363.63 | 11 |  | 179999.93 | 339000.07 | INV-SUP-011
2.12 | 2025-11-26 | Material | Aluminum Roofing Sheets (Corrugated, 3m) | 927000 |  | 61.8 |  | 585400 | 341600 | INV-SUP-012
2.13 | 2025-12-06 | Material | Galvanized Piping & Fittings (1.5" & 2") | 90000 |  | 6 |  | 75000 | 15000 | INV-SUP-013
2.14 | 2025-12-06 | Material | 80A Circuit Breaker (ABB 100 Amp) | 45000 |  | 1 |  | 100000 | -55000 | INV-SUP-014
2.15 | 2025-12-06 | Material | 25mm x 4-Core Flexible Cable | 315000 |  | 15 |  | 250000 | 65000 | INV-SUP-015
2.16 | 2025-12-06 | Material | cable lugs 35mm & 50mm, cable glands | 3200 |  | 8 |  | 22300 | -19100 | INV-SUP-016
2.17 |  | Material | Paint / Anti-corrosion Coating (Primer + Top) | 120000 |  | 4 |  | 9000 | 111000 | INV-SUP-017
2.18 |  | Material | QA/QC Materials (Molds, Slump Cone, Sheets) | 50000 |  | 1 |  | 0 | 50000 | INV-SUP-018
2.19 |  | Material | Consumables (Rods, discs, bolts, nuts, sealants) | 150000 |  | 1 |  | 36000 | 114000 | INV-SUP-019
|  |  |  | 4952200 | 511549.976 |  |  | 3216599.8499 | 1735600.1501
S/N | Date | WBS Category | Item Description (Detailed) | Budgeted Total Cost (NGN) | Actual Unit Cost (NGN) | Actual Quantity | Commitment/LPO Amount (NGN) | Actual Paid Amount (NGN) | Cost Variance (NGN) | Document Reference (Invoice/PV) | Notes/Justification
3 | - | Equipment / Tools | - | 730500 | 313450 | Days | 0 | 602900 | 127600 | - | -
3.1 |  | Equipment | Manual Forklift | 20000 |  | 1 |  | 0 | 20000 | LPO-RENT-001 | Rental LPO issued for 12 days
3.2 | 2025-11-17 | Equipment | Concrete Mixer, Vibrator (Handheld, electric) & equipment/ Mob and Demob | 127000 | 127000 | 1 |  | 127000 | 0 | LPO-RENT-002
3.3 |  | Equipment | Welding Machine (300A capacity) | 20000 |  | 5 |  | 0 | 20000 | LPO-RENT-003
3.4 |  | Equipment | Grinding Machine (9" disc) | 16000 |  | 4 |  | 0 | 16000 | LPO-RENT-004
3.5 |  | Equipment | Drilling Machine (Corded / impact type) | 16000 |  | 4 |  | 0 | 16000 | LPO-RENT-005
3.6 |  | Equipment | Spanners & Socket Sets (up to 32mm) | 0 | 0 | 1 |  | 0 | 0 | LPO-RENT-006
3.7 |  | Equipment | Pipe Wrench & Threading Tools (Up to 2") | 16000 | 8000 | 2 |  | 16000 | 0 | LPO-RENT-007
3.8 |  | Equipment | Measuring Tape | 6000 | 6000 | 1 |  | 6000 | 0 | LPO-RENT-008
3.9 |  | Equipment | Scaffold / Ladder (Certified type) | 15000 |  | 10 |  | 0 | 15000 | LPO-RENT-009
3.1 |  | Equipment | Electric Testers / Multimeter | 15000 |  | 1 |  | 0 | 15000 | INV-E-009
3.11 |  | Equipment | Hand Tools (Hammers, , etc.) | 5000 | 5000 | 1 |  | 5000 | 0 | INV-PPE-008
3.12 | 2025-11-10 | Equipment | Hand Tools (Shovels, Headpans & diggers) | 45000 | 41000 | 1 |  | 41000 | 4000 | INV-PPE-007
3.13 | 2025-11-10 | Equipment | PPE - Helmet (For 15 Personnel) | 60000 | 6000 | 7 |  | 42000 | 18000 | INV-PPE-006
3.14 | 2025-11-10 | Equipment | PPE - Gloves (For 15 Personnel) | 10000 | 1200 | 12 |  | 14400 | -4400 | INV-PPE-005
3.15 | 2025-11-10 | Equipment | PPE - Boots (For 15 Personnel) | 75000 | 15000 | 5 |  | 75000 | 0 | INV-PPE-004
3.16 | 2025-11-10 | Equipment | PPE - Coverall (For 15 Personnel) | 120000 | 15000 | 7 |  | 105000 | 15000 | INV-PPE-003
3.17 | 2025-11-25 | Equipment | PPE - Harness (Assumed 2 for height) | 30000 | 30000 | 1 |  | 30000 | 0 | INV-PPE-002
3.18 | 2025-11-10 | Equipment | PPE - Goggles/Earplugs (For 15 Personnel) | 2500 | 1250 | 10 |  | 12500 | -10000 | INV-PPE-001
3.19 | 2025-11-10 | Equipment | Nose Mask | 12000 | 8000 | 1 |  | 8000 | 4000 | INV-PPE-000
3.2 | 2025-11-15 | Equipment | First Aid Box (HSE compliant) |  | 0 | 1 |  | 0 | 0 | INV-FBOX-001 | Boots price higher than budget
3.21 |  | Equipment | Barricades / Safety Cones / Signs |  | 0 | 0 |  | 0 | 0 | INV-CAUTION-002
3.23 |  | Equipment | Wheelbarrows (Re-inforced) | 120000 | 50000 | 2 |  | 100000 | 20000 | INV-WB-003
| 2025-11-10 | Equipment | mason hammer | 0 | 5000 | 1 |  | 5000 | -5000
| 2025-11-10 |  | Digger | 0 | 4000 | 2 |  | 8000 | -8000
| 2025-11-10 | Equipment | havy duty hammer | 0 | 8000 | 1 |  | 8000 | -8000
|  |  |  | 730500 | 330450 |  | 0 | 602900 | 127600
S/N | Date | WBS Category | Item Description (Detailed) | Budgeted Total Cost (NGN) | Actual Unit Cost (NGN) | Actual Quantity | Commitment/LPO Amount (NGN) | Actual Paid Amount (NGN) | Cost Variance (NGN) | Document Reference (Invoice/PV) | Notes/Justification
4 | - | Logistics & Mobilization | - | 250000 | - |  | - | 700850 | -450850 | - | -
4.1 |  | Logistics | Fuel/ Refill (Generator) and (Vehicle) | 415500 | 1020 | 407.3529 | - | 435500 | -20000 | Receipt-Fuel-00 | Draw down from Fuel budget
4.1.1 | 2025-11-05 | Logistics | Fuel (vehicle) | 20000 | 1020 | 19.6078 |  | 20000 | 0 | Receipt-Fuel-001
4.1.2 | 2025-11-10 | Logistics | Fuel (vehicle) | 10000 | 1020 | 9.8039 |  | 10000 | 0 | Receipt-Fuel-002
4.1.3 | 2025-11-11 | Logistics | Fuel (vehicle) | 10000 | 1020 | 9.8039 |  | 10000 | 0 | Receipt-Fuel-003
4.1.4 | 2025-11-12 | Logistics | Fuel (vehicle) | 15000 | 1020 | 14.7059 |  | 15000 | 0 | Receipt-Fuel-004
4.1.5 | 2025-11-13 | Logistics | Fuel (vehicle) | 20000 | 1020 | 19.6078 |  | 20000 | 0 | Receipt-Fuel-005
4.1.6 | 2025-11-14 | Logistics | Fuel (vehicle) | 15000 | 1020 | 14.7059 |  | 15000 | 0 | Receipt-Fuel-006
4.1.7 | 2025-11-15 | Logistics | Fuel (vehicle) | 10000 | 1020 | 9.8039 |  | 10000 | 0 | Receipt-Fuel-007
4.1.8 | 2025-11-17 | Logistics | Fuel (vehicle) | 20000 | 1020 | 19.6078 |  | 20000 | 0 | Receipt-Fuel-008
4.1.9 | 2025-11-18 | Logistics | Fuel (vehicle) | 10000 | 1020 | 9.8039 |  | 10000 | 0 | Receipt-Fuel-009
4.1.10 | 2025-11-19 | Logistics | Fuel (vehicle) | 20000 | 1020 | 19.6078 |  | 20000 | 0 | Receipt-Fuel-010
4.1.11 | 2025-11-20 | Logistics | Fuel (vehicle) | 15000 | 1020 | 14.7059 |  | 15000 | 0 | Receipt-Fuel-011
4.1.12 | 2025-11-21 | Logistics | Fuel (vehicle) | 20000 | 1020 | 19.6078 |  | 20000 | 0 | Receipt-Fuel-012
4.1.13 | 2025-11-23 | Logistics | Fuel (vehicle) | 15000 | 1020 | 14.7059 |  | 15000 | 0 | Receipt-Fuel-013
4.1.14 | 2025-11-24 | Logistics | Fuel (vehicle) | 20000 | 1020 | 19.6078 |  | 20000 | 0 | Receipt-Fuel-014
4.1.15 | 2025-11-25 | Logistics | Fuel (vehicle) | 15000 | 1020 | 14.7059 |  | 15000 | 0 | Receipt-Fuel-015
4.1.16 | 2025-11-26 | Logistics | Fuel (vehicle) | 15000 | 1020 | 14.7059 |  | 15000 | 0 | Receipt-Fuel-016
4.1.17 | 2025-11-27 | Logistics | Fuel (vehicle) | 10000 | 1020 | 9.8039 |  | 10000 | 0 | Receipt-Fuel-017
4.1.18 | 2025-11-28 | Logistics | Fuel (vehicle) | 15000 | 1020 | 14.7059 |  | 15000 | 0 | Receipt-Fuel-018
4.1.19 | 2025-11-29 | Logistics | Fuel (vehicle) | 20000 | 1020 | 19.6078 |  | 20000 | 0 | Receipt-Fuel-019
4.1.20 | 2025-12-01 | Logistics | Fuel (vehicle) | 15000 | 1020 | 14.7059 |  | 15000 | 0 | Receipt-Fuel-020
4.1.21 | 2025-12-02 | Logistics | Fuel (vehicle) | 10000 | 1020 | 9.8039 |  | 10000 | 0 | Receipt-Fuel-021
4.1.22 | 2025-12-04 | Logistics | Fuel (vehicle) | 20000 | 1020 | 19.6078 |  | 20000 | 0 | Receipt-Fuel-022
4.1.23 | 2025-12-06 | Logistics | Fuel (vehicle) | 10000 | 1020 | 9.8039 |  | 10000 | 0 | Receipt-Fuel-023
4.1.24 | 2025-12-08 | Logistics | Fuel (vehicle) | 25000 | 1020 | 24.5098 |  | 25000 | 0 | Receipt-Fuel-024
4.1.25 | 2025-12-12 | Logistics | Fuel (vehicle) | 25500 | 1020 | 25 |  | 25500 | 0 | Receipt-Fuel-025
4.1.26 |  | Logistics | Fuel (vehicle) |  |  |  |  | 0 | #VALUE! | Receipt-Fuel-026
4.1.27 |  | Logistics | Fuel (vehicle) |  |  |  |  | 0 | 0 | Receipt-Fuel-027
4.1.28 |  | Logistics | Fuel (vehicle) |  |  |  |  | 0 | 0 | Receipt-Fuel-028
4.1.29 |  | Logistics | Fuel (vehicle) |  |  |  |  | 0 | 0
4.1.2.0 |  | Logistics | Office Operational power cost |  | 1020 | 0 |  | 0 | 0
4.1.2.1 | 2025-11-07 | Logistics | Fuel (Generator Office) | 5000 | 1020 | 4.902 |  | 5000 | 0 | Receipt-Fuel-003
4.1.2.2 | 2025-11-08 | Logistics | Fuel (Generator Office) | 5000 | 1020 | 4.902 |  | 5000 | 0 | Receipt-Fuel-004
4.1.2.3 | 2025-11-10 | Logistics | Fuel (Generator Office) | 5000 | 1020 | 4.902 |  | 5000 | 0 | Receipt-Fuel-005
4.1.2.4 | 2025-11-18 | Logistics | Fuel (Generator Office) | 3000 | 1020 | 2.9412 |  | 3000 | 0
4.1.2.5 | 2025-11-22 | Logistics | Fuel (Generator Home) | 5000 | 1020 | 4.902 |  | 5000 | 0
4.1.2.6 | 2025-11-25 | Logistics | Fuel (Generator Home) | 5000 | 1020 | 4.902 |  | 5000 | 0
4.1.2.7 | 2025-11-26 | Logistics | Fuel (Generator Office) | 3000 | 1020 | 2.9412 |  | 3000 | 0
4.1.2.8 | 2025-11-29 | Logistics | Fuel (Generator Home) | 4000 | 1020 | 3.9216 |  | 4000 | 0
4.2 |  | Logistics | Vehicle Maintenance | 25900 |  |  | - | 185900 | -160000 | PV-MAINT-00 | Emergency, unbudgeted repair
4.2.1 | 2025-11-05 | Logistics | Vehicle Maintenance ( Car Oil) | 8000 | 4000 | 2 |  | 8000 | 0 | PV-MAINT-001
4.2.2 | 2025-11-06 | Logistics | Vehicle Maintenance (battery & Battery Terminal) | 5000 | 5000 | 1 |  | 5000 | 0 | PV-MAINT-002
4.2.3 | 2025-11-11 | Logistics | Vehicle Maintenance (Car Oil) | 4000 | 4000 | 1 |  | 4000 | 0 | PV-MAINT-003
4.2.4 | 2025-11-11 | Logistics | pump tire | 500 | 500 | 1 |  | 500 | 0 | PV-MAINT-004
4.2.5 | 2025-11-13 | Logistics | pump tire | 400 | 400 | 1 |  | 400 | 0 | PV-MAINT-005
4.2.6 | 2025-11-17 | Logistics | Vehicle Maintenance (Car Oil) | 4000 | 4000 | 1 |  | 4000 | 0 | PV-MAINT-006
4.2.7 | 2025-11-18 | Logistics | Vehicle Maintenance (tire repair) | 2500 | 2500 | 1 |  | 2500 | 0 | PV-MAINT-007
4.2.8 | 2025-11-19 | Logistics | Vehicle Maintenance (tire repair) | 1500 | 1500 | 1 |  | 1500 | 0 | PV-MAINT-008
4.2.9 | 2025-11-24 | Logistics | Vehicle Maintenance (Car Oil) | 4000 | 4000 | 1 |  | 4000 | 0 | PV-MAINT-009
4.2.10 | 2025-11-25 | Logistics | Vehicle Maintenance (tire repair) | 2000 | 2000 | 1 |  | 2000 | 0 | PV-MAINT-010
4.2.11 | 2025-11-26 | Logistics | vehicle Maintainance ( Car Oil) | 4000 | 4000 | 1 |  | 4000 | 0
4.2.12 | 2025-11-27 | Logistics | vehicle Maintainance | 150000 | 150000 | 1 |  | 150000 | 0
vehicle Maintainance
vehicle Maintainance
vehicle Maintainance
vehicle Maintainance
4.3 |  | Logistics | Local Transport Fees (Staff daily shuttle) | 13500 |  | Days | - | 79450 | -65950 | PV-TRANS-00 | Ad-hoc transport to and from office
4.3.1 | 2025-11-07 | Logistics | Local Transport Fees (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-001 | Ad-hoc transport to and from office
4.3.2 | 2025-11-08 | Logistics | Local Transport Fees (Staff daily shuttle) | 1500 | 1500 | 1 |  | 1500 | 0 | PV-TRANS-002 | Ad-hoc transport to and from office
4.3.3 | 2025-11-10 | Logistics | Local Transport Fees (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-003 | Ad-hoc transport to and from office
4.3.4 | 2025-11-11 | Logistics | Local Transport Fees (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-004 | Ad-hoc transport to and from office
4.3.5 | 2025-11-12 | Logistics | Local Transport Fees (Staff shuttle to Site-Afam) | 8000 | 2600 | 3 |  | 7800 | 200 | PV-TRANS-005 | Ad-hoc transport to and from office
4.3.6 | 2025-11-13 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-006 | Ad-hoc transport to and from office
4.3.7 | 2025-11-14 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-007 | Ad-hoc transport to and from office
4.3.8 | 2025-11-15 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-008
4.3.9 | 2025-11-16 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 2 |  | 2000 | -1000 | PV-TRANS-009
4.3.10 | 2025-11-17 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-010
4.3.11 | 2025-11-18 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 2 |  | 2000 | -1000 | PV-TRANS-011
4.3.12 | 2025-11-19 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-012
4.3.13 | 2025-11-20 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-013
4.3.14 | 2025-11-21 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-014
4.3.15 | 2025-11-22 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-015
4.3.16 | 2025-11-23 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-016
4.3.17 | 2025-11-24 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-017
4.3.18 | 2025-11-25 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-018
4.3.19 | 2025-11-26 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-019
4.3.20 | 2025-11-27 | Logistics | Local Transport fairs (Staff daily shuttle) | 1000 | 1000 | 1 |  | 1000 | 0 | PV-TRANS-020
4.3.21 | 2025-12-01 | Logistics | Local Transport fairs (Staff daily shuttle) | 5250 | 1750 | 3 |  | 5250 | 0 | PV-TRANS-021
4.3.22 | 2025-12-03 | Logistics | Local Transport fairs (Staff daily shuttle) | 3500 | 3500 | 1 |  | 3500 | 0
4.3.23 | 2025-12-06 | Logistics | Local Transport fairs (Staff daily shuttle) | 6700 | 3350 | 2 |  | 6700 | 0
4.3.24 | 2025-12-09 | Logistics | Local Transport fairs (Staff daily shuttle)& transport for crimping tool | 15400 | 7700 | 2 |  | 15400 | 0
4.3.25 | 2025-12-10 | Logistics | Local Transport fairs (Staff daily shuttle) | 12600 | 4200 | 3 |  | 12600 | 0
4.3.26 | 2025-12-11 | Logistics | Local Transport fairs (Staff daily shuttle) | 6700 | 3350 | 2 |  | 6700 | 0
|  |  |  | 250000 |  |  |  | 700850 | -450850
S/N | Date | WBS Category | Item Description (Detailed) | Budgeted Total Cost (NGN) | Actual Unit Cost (NGN) | Actual Quantity | Commitment/LPO Amount (NGN) | Actual Paid Amount (NGN) | Cost Variance (NGN) | Document Reference (Invoice/PV) | Notes/Justification
5 | - | Accommodation & Welfare | - | 300000 | - | - | - | 264399.5 | 35600.5 | - | -
5.1 |  | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3000 | Persons | - | 264399.5 | -255899.5 | PV-FEED-00 | Required for productivity
5.1.1 | 2025-11-05 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2000 | 4 |  | 8000 | 500 | PV-FEED-001
5.1.2 | 2025-11-07 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2000 | 2 |  | 4000 | 4500 | PV-FEED-002
5.1.3 | 2025-11-08 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2000 | 2 |  | 4000 | 4500 | PV-FEED-003
5.1.4 | 2025-11-10 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3800 | 2 |  | 7600 | 900 | PV-FEED-004
5.1.5 | 2025-11-11 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2500 | 4 |  | 10000 | -1500 | PV-FEED-005
5.1.6 | 2025-11-12 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2700 | 4 |  | 10800 | -2300 | PV-FEED-006
5.1.7 | 2025-11-13 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2500 | 4 |  | 10000 | -1500 | PV-FEED-007
5.1.8 | 2025-11-14 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3875 | 4 |  | 15500 | -7000 | PV-FEED-008
5.1.9 | 2025-11-15 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2040 | 5 |  | 10200 | -1700 | PV-FEED-009
5.1.10 | 2025-11-16 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3500 | 1 |  | 3500
5.1.11 | 2025-11-17 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2966.5 | 3 |  | 8899.5 | -399.5 | PV-FEED-010
5.1.12 | 2025-11-18 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3500 | 3 |  | 10500 | -2000 | PV-FEED-011
5.1.13 | 2025-11-19 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3000 | 3 |  | 9000 | -500 | PV-FEED-012
5.1.14 | 2025-11-20 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3700 | 2 |  | 7400 | 1100 | PV-FEED-013
5.1.15 | 2025-11-21 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3700 | 2 |  | 7400 | 1100 | PV-FEED-014
5.1.16 | 2025-11-22 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3700 | 2 |  | 7400 | 1100 | PV-FEED-015
5.1.17 | 2025-11-23 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3700 | 2 |  | 7400 | 1100 | PV-FEED-016
5.1.18 | 2025-11-24 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3500 | 2 |  | 7000 | 1500 | PV-FEED-017
5.1.19 | 2025-11-25 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3500 | 2 |  | 7000 | 1500 | PV-FEED-018
5.1.20 | 2025-11-26 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3500 | 2 |  | 7000 | 1500 | PV-FEED-019
5.1.21 | 2025-11-27 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 4000 | 2 |  | 8000 | 500 | PV-FEED-020
5.1.22 | 2025-11-28 | Welfare | Staff Feeding (Daily stipend/provision) paid arias of staff labourers feeding | 8500 | 2680 | 5 |  | 13400 | -4900 | PV-FEED-021
5.1.23 | 2025-11-29 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2800 | 3 |  | 8400 | 100 | PV-FEED-022
5.1.24 | 2025-11-30 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3000 | 1 |  | 3000 | 5500 | PV-FEED-023
5.1.25 | 2025-12-01 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3500 | 2 |  | 7000 | 1500 | PV-FEED-024
5.1.26 | 2025-12-02 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3500 | 2 |  | 7000 | 1500 | PV-FEED-025
5.1.27 | 2025-12-03 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 4000 | 1 |  | 4000 | 4500 | PV-FEED-026
5.1.28 | 2025-12-04 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3000 | 3 |  | 9000 | -500 | PV-FEED-027
5.1.29 | 2025-12-05 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3500 | 1 |  | 3500 | 5000 | PV-FEED-028
5.1.30 | 2025-12-06 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 4500 | 1 |  | 4500 | 4000 | PV-FEED-029
5.1.31 | 2025-12-08 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2000 | 3 |  | 6000 | 2500
5.1.32 | 2025-12-09 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2100 | 3 |  | 6300 | 2200
5.1.33 | 2025-12-10 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2100 | 3 |  | 6300 | 2200
5.1.34 | 2025-12-11 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2000 | 2 |  | 4000 | 4500
5.1.35 | 2025-12-12 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 2800 | 3 |  | 8400 | 100
5.1.36 | 2025-12-13 | Welfare | Staff Feeding (Daily stipend/provision) | 8500 | 3000 | 1 |  | 3000 | 5500
5.1.37 |  | Welfare | Staff Feeding (Daily stipend/provision) | 8500 |  |  |  | 0 | 8500
5.1.38 |  |  | Staff Feeding (Daily stipend/provision) | 8500 |  |  |  | 0 | 8500
|  |  |  | 300000 |  |  |  | 264399.5 | 35600.5
S/N | Date | WBS Category | Item Description (Detailed) | Budgeted Total Cost (NGN) | Actual Unit Cost (NGN) | Actual Quantity | Commitment/LPO Amount (NGN) | Actual Paid Amount (NGN) | Cost Variance (NGN) | Document Reference (Invoice/PV) | Notes/Justification
6 | Date | Accommodation | - | 600000 |  | - | - | 0 | 600000 | - | -
6.1 |  | Accommodation | Housing/Site Office Rental (Weekly Payment) | 240000 |  | Day |  | 0 | 240000 | INV-RENT-00 | Weekly rental fee paid
6.1.1 |  | Accommodation | Housing/Site Office Rental (Weekly Payment) | 40000 |  | 1 |  | 0 | 40000 | INV-RENT-001
6.1.2 |  | Accommodation | Housing/Site Office Rental (Weekly Payment) | 40000 |  | 1 |  | 0 | 40000 | INV-RENT-002
6.1.3 |  | Accommodation | Housing/Site Office Rental (Weekly Payment) | 40000 |  | 1 |  | 0 | 40000 | INV-RENT-003
6.1.4 |  | Accommodation | Housing/Site Office Rental (Weekly Payment) | 40000 |  | 1 |  | 0 | 40000 | INV-RENT-004
6.1.5 |  | Accommodation | Housing/Site Office Rental (Weekly Payment) | 40000 |  | 1 |  | 0 | 40000 | INV-RENT-005
6.1.6 |  | Accommodation | Housing/Site Office Rental (Weekly Payment) | 40000 |  | 1 |  | 0 | 40000 | INV-RENT-006
|  |  |  | 600000 |  |  |  | 0 | 600000
S/N | Date | WBS Category | Item Description (Detailed) | Budgeted Total Cost (NGN) | Actual Unit Cost (NGN) | Actual Quantity | Commitment/LPO Amount (NGN) | Actual Paid Amount (NGN) | Cost Variance (NGN) | Document Reference (Invoice/PV) | Notes/Justification
| Date |  |  | 409135 |  |  |  | 584100 | -174965
7.1 | 2025-11-05 | Contingency Draw 9PR) | Fipl security pesonnel lunch | UNBUDGETED | 2000 | 1 |  | 2000 | #VALUE!
7.2 | 2025-11-10 | Contingency Draw ( Service charge) | Transfer Service charge | UNBUDGETED | 2500 | 1 |  | 2500 | #VALUE!
| 2025-11-10 | Contingency Draw (Logistics) | Transportation for Cement | UNBUDGETED | 55000 | 1 |  | 55000 | #VALUE!
7.3 | 2025-11-13 | Contingency Draw (Equipment (tool)) | ANTICHOC PLUM | UNBUDGETED | 7000 | 1 |  | 7000 | #VALUE!
7.4 | 2025-11-13 | Contingency Draw (Material) | 10 MM Rebar | UNBUDGETED | 7500 | 3 |  | 22500 | #VALUE!
7.5 | 2025-11-13 | Contingency Draw | concrete nail | UNBUDGETED | 5600 | 1 |  | 5600 | #VALUE!
7.6 | 2025-11-12 | Contingency Draw | 2 by 4 wood | UNBUDGETED | 1200 | 5 |  | 6000 | #VALUE!
7.7 | 2025-11-12 | Contingency Draw | 2 by 3 wood | UNBUDGETED | 1200 | 10 |  | 12000 | #VALUE!
7.8 | 2025-11-12 | Contingency Draw | 3 inches nail | UNBUDGETED | 1000 | 3 |  | 3000 | #VALUE!
7.9 | 2025-11-12 | Contingency Draw | printing Method Statement, Drawing and JHA | UNBUDGETED | 250 | 25 |  | 6250 | #VALUE!
7.1 | 2025-11-12 | Contingency Draw | balance for cleaning of the site workshop space | UNBUDGETED | 6000 | 1 |  | 6000 | #VALUE!
7.11 | 2025-11-13 | Contingency Draw | Chistle blinding cutting | UNBUDGETED | 3000 | 1 |  | 3000 | #VALUE!
| 2025-11-14 | Contingency Draw | purchase of Pinches, broom, | UNBUDGETED | 3000 | 1 |  | 3000 | #VALUE!
7.12 | 2025-11-14 | Contingency Draw | payment for extra 2by2 soft wood, 1.5 inch nail, sawing of the wood, and logistics. | UNBUDGETED | 8300 | 1 |  | 8300 | #VALUE!
| 2025-11-15 | Contingency Draw | Polystyrene / Expansion joint material | UNBUDGETED | 14500 | 1 |  | 14500 | #VALUE!
7.13 | 2025-11-15 | Contingency Draw | nails (2 inch, concrete one pack & wire one pound) | UNBUDGETED | 3200 | 1 |  | 3200 | #VALUE!
7.14 | 2025-11-17 | Contingency Draw (Tool) | Trowel,plastic bucket | UNBUDGETED | 5000 | 1 |  | 5000 | #VALUE!
7.15 | 2025-11-17 | Contingency Draw (PR) | Logistics for client Supervisore. | UNBUDGETED | 3000 | 1 |  | 3000 | #VALUE!
7.16 | 2025-11-19 | Contingency Draw (Material) | 8mm High tension rod | UNBUDGETED | 4300 | 2 |  | 8600 | #VALUE!
7.17 | 2025-11-19 | Contingency Draw (Logistics) | Transportation for shelter materials | UNBUDGETED | 25000 | 1 |  | 25000 | #VALUE!
| 2025-11-19 | Contingency Draw (Logistics) | purchase of extra 8mm rod | UNBUDGETED | 4300 | 2 |  | 8600 | #VALUE!
7.18 | 2025-11-20 | Contingency Draw (Material) | Additional Granite | UNBUDGETED | 4500 | 5 |  | 22500 | #VALUE!
7.19 | 2025-11-20 | Contingency Draw (Transfer charges and granite loadersl) | Transfer Service charge and granite loaders | UNBUDGETED | 1300 | 1 |  | 1300 | #VALUE!
7.2 | 2025-11-21 | Contingency Draw | water for drinking | UNBUDGETED | 400 | 1 |  | 400 | #VALUE!
7.21 | 2025-11-24 | Contingency Draw | water for drinking | UNBUDGETED | 400 | 1 |  | 400 | #VALUE!
7.22 | 2025-11-26 | Contingency Draw | fuel for work at home | UNBUDGETED | 5000 | 1 |  | 5000 | #VALUE!
7.23 | 2025-11-27 | Contingency Draw | PR for roof procurment workers | UNBUDGETED | 3000 | 1 |  | 3000 | #VALUE!
7.24 | 2025-11-27 | Contingency Draw | Transportation of roffing sheets to site | UNBUDGETED | 20000 | 1 |  | 20000 | #VALUE!
7.25 | 2025-11-28 | Contingency Draw | Drilling Bits ( Metal) | UNBUDGETED | 1500 | 5 |  | 7500 | #VALUE!
7.26 | 2025-11-29 | Contingency Draw | capenter payment for foundation step | UNBUDGETED | 15000 | 1 |  | 15000 | #VALUE!
7.27 | 2025-12-02 | Contingency Draw | dampper materials | UNBUDGETED | 16800 | 3 |  | 50400 | #VALUE!
7.28 | 2025-12-02 | Contingency Draw | concrete drilling bit (2), spanners (2), concrete expantion bolts, dampper cutting and whashing | UNBUDGETED | 19300 | 1 |  | 19300 | #VALUE!
7.29 | 2025-12-02 | Contingency Draw | payment for the labour to transfer the compressor machine from the storage area to the testing area | UNBUDGETED | 2500 | 8 |  | 20000 | #VALUE!
7.3 | 2025-12-04 | Contingency Draw | fix drilling bit | UNBUDGETED | 1000 | 1 |  | 1000 | #VALUE!
7.31 | 2025-12-06 | Contingency Draw | Bolts and clamp for pipe intergrity | UNBUDGETED | 16000 | 1 |  | 16000 | #VALUE!
7.32 | 2025-12-08 | Contingency Draw | Hole Bit & cup | UNBUDGETED | 16000 | 1 |  | 16000 | #VALUE!
| 2025-12-08 | Contingency Draw | carrot stone stenless | UNBUDGETED | 12000 | 1 |  | 12000 | #VALUE!
| 2025-12-08 | Contingency Draw | Grinding stone | UNBUDGETED | 3000 | 1 |  | 3000 | #VALUE!
| 2025-12-08 | Contingency Draw | square | UNBUDGETED | 3000 | 1 |  | 3000 | #VALUE!
| 2025-12-08 | Contingency Draw | cutting disc metal | UNBUDGETED | 1000 | 2 |  | 2000 | #VALUE!
| 2025-12-08 | Contingency Draw | Transfer of compressor into the Shelter | UNBUDGETED | 60000 | 1 |  | 60000 | #VALUE!
| 2025-12-09 | Contingency Draw | crimping tool hirering | UNBUDGETED | 15000 | 1 |  | 15000 | #VALUE!
| 2025-12-10 | Contingency Draw | payment for treading of pipe and hiring of trading tool | UNBUDGETED | 15000 | 1 |  | 15000 | #VALUE!
| 2025-12-10 | Contingency Draw | bank charges and pos withdrawal charges | UNBUDGETED | 5000 | 1 |  | 5000
7.33 | 2025-12-11 | Contingency Draw | hHose, clip and paint brush | UNBUDGETED | 1250 | 1 |  | 1250 | #VALUE!
7.25 | 2025-12-12 | Contingency Draw | public Relations: Safty, Security, Armed Security | UNBUDGETED | 30000 | 1 |  | 30000 | #VALUE!
| 2025-12-12 |  | public Relations: Plant Mgr And Plant Supervisor |  | 30000 | 1 |  | 30000 | -30000
TOTALS |  |  |  | 409135 |  |  |  | 584100 | -174965
Total of Budget, Actual Amount Spent and the Variation
|  |  |  | Budgeted Total Cost (NGN) |  |  |  | Actual Paid Amount (NGN) | Cost Variance (NGN)
TOTALS | - | - | - | 8607835 |  | - |  | 6276849.3499 | 2330985.6501 | - | -
Project Financial Control Summary
This section links the actual expenditure back to the original budget for financial oversight.
Financial Metric | Total Budgeted Cost (NGN) | Total Committed/LPO (NGN) | Total Actual Paid (NGN) | Variance (Budget vs. Paid) (NGN) | % Variance
1.0 Human Resources (H/R) | 1366000 | 0 | 908000 | 488000 | 35.72%
2.0 Material Requirements | 4952200 | 0 | 3216599.8499 | 1735600.1501 | 35.05%
3.0 Equipment/Tools | 730500 | 0 | 602900 | 127600 | 17.47%
4.0 Logistics | 250000 | 0 | 700850 | -450850 | -180.3%
5.0 Welfare | 300000 | 0 | 264399.5 | 35600.5 | 11.87%
6.0 Accommodation | 600000 | 0 | 0 | 600000 | 100%
5.0 Contingencies (5%) | 409135 | 0 | 584100 | -174965 | -42.76%
TOTAL PROJECT COST BASE | 8607835 | 0 | 6276849.3499 | 2360985.6501 | 27.43%
BUDGET FUNDS RECEIVED
S/N | DATE | RECEIVED FROM | DESCRIPTION | TYPE | AMOUNT NGN
1 | 2025-11-07 | Kingsley Etim | Miscellaneouse | Bank Transfer | 50000
2 | 2025-11-10 | SEESL | Material procumen | Bank Transfer | 2000000
3 | 2025-11-10 | Emeke Olumor | Material procumen | Bank Transfer | 1000000
4 | 2025-11-18 | SEESL | Material procumen | Bank Transfer | 1260000
5 | 2025-11-20 | Emeke Olumor | Material procumen | Cash | 3800
6 | 2025-11-21 | Emeke Olumor | Material procumen | Cash | 1000
7 | 2025-11-25 | SEESL | Material procumen | Bank Transfer | 500000
8 | 2025-11-26 | Emeke Olumor | Manpower H/R | Bank Transfer | 80000
9 | 2025-12-03 | SEESL | Job completion | Bank Transfer | 414000 | Deducted the unpaid balance of N86,000 from the returned Angle Irons from the paid in N500,000 sent.
10 | 2025-12-08 | SEESL | Dept payment | Bank Transfer TO Olumor | 497300
11 | 2025-12-12 | SEESL | PR | Cash | 30000
TOTAL MONEY RECIVED |  |  |  |  | 5836100
TOTAL DEPT |  |  |  |  | 0
TOTAL MONEY SPENT (minus total not paid) |  |  |  |  | 6276849.3499
ACCOUNT BALANCE |  |  |  |  | -440749.3499
Guide to Using the Expense Tracker
1. WBS Category: Use the official categories from the budget (H/R, Material, Equipment, Logistics, Welfare, Contingency).
2. Budgeted Total Cost (NGN): This is the total planned expenditure for the entire WBS line (e.g., the total NGN 3,240,000 for H/R), copied from the comprehensive budget. This allows quick comparison.
3. Actual Unit Cost & Quantity: Record the exact unit cost and quantity you paid for (e.g., N6,200 per bag for 32 bags of cement).
4. Commitment/LPO Amount (NGN): This is the value of any Legally Committed spending (e.g., a Local Purchase Order/Contract) that has been issued but not yet paid. This is crucial for managing cash flow.
5. Actual Paid Amount (NGN): The money that has left the company's account.
6. Cost Variance (NGN): This is the most important column for control. It is calculated as: (Budgeted Cost of Item) - (Actual Cost of Item).
For new, unforeseen expenses (like the flat tire repair), the Budgeted Total Cost column remains blank or is noted as "Unbudgeted."
The variance for these items will be highly negative (equal to the total paid amount).
These items must be funded by drawing down from the Contingencies budget (Row 6.1). You record the total amount transferred from Contingency to cover these unbudgeted costs.
Key Control Notes:
1. Commitment Tracking: The Commitment/LPO Amount column is crucial for tracking potential liabilities (money promised but not yet paid), preventing unauthorized overspending before actual payment.
2. Variance Analysis: A negative variance indicates an overrun (e.g., buying cement for N6,200 instead of the budgeted N6,000). A positive variance indicates a saving.
3. Contingency Management: All variances exceeding 10% on a WBS category should be noted and reported to management. Any draw-down from the Contingencies budget must be formally approved and logged as an expense against the Contingency line.